## Dashboard
IMMERSIVE EGO: CIVITAS — PROJECT CONTROL
Minecraft 1.21.1 • NeoForge • Java 21 • GPL-3.0-only
ROADMAP PHASES |  | BACKLOG TASKS |  | STORY POINTS |  | OPEN RISKS
19 |  | 151 |  | 1396 |  | 25
MILESTONES |  | P0 TASKS |  | TEST CASES |  | RELEASE CHECKS
15 |  | 91 |  | 24 |  | 25
BACKLOG COMPLETION |  |  |  | CRITICAL ARCHITECTURE PATH
0% |  |  |  | P0 → P1 → P2 → P3 → P4 → P5 → P6 → P7
ROADMAP PHASE LOAD
Phase | Title | Milestone | Story Points |  | RELEASE GUARDRAILS
P0 | Governance, legal audit, source pinning | M0 | 40 |  | 1 | No copied upstream assets/logos
P1 | NeoForge integration harness | M1 | 44 |  | 2 | Every adapted file has provenance
P2 | Immersive EGO external subject API | M1 | 26 |  | 3 | Atomic restart-repairable transactions
P3 | Unified resident kernel | M2 | 47 |  | 4 | MCA stays family/social authority
P4 | MineColonies civic bridge | M3 | 100 |  | 5 | MineColonies stays civic authority
P5 | MCA social bridge | M4 | 76 |  | 6 | EGO stays body/mind authority
P6 | Modern Companions military bridge | M5 | 87 |  | 7 | Dedicated-server and migration gates
P7 | Desert colony vertical slice | M6 | 97 |  | 8 | P7 before broad politics/economy
P8 | Unified jobs and professions | M7 | 61
P9 | Resource requests and logistics | M7 | 73
P10 | NPC work recipes | M8 | 71
P11 | Factions, cultures and reputation | M9 | 81
P12 | Economy, trade and contracts | M9 | 84
P13 | Defense, raids and command | M10 | 79
P14 | Households, family and education | M11 | 79
P15 | Governance, law, crime and migration | M11 | 89
P16 | Crises and diplomacy | M12 | 84
P17 | UI, configuration and performance | M13 | 94
P18 | Hardening and release | M14 | 84

## Roadmap
Order | Phase | Title | Milestone | Objective | Status | Priority | Story Points | Task Count | Depends On | Exit Gate | Release Train
0 | P0 | Governance, legal audit, source pinning | M0 | Establish GPL governance, exact source mapping, provenance and asset controls. | Not Started | P0 | 40 | 7 |  | GPL repo, dependency audit and provenance gates pass. | Internal Gate
1 | P1 | NeoForge integration harness | M1 | Boot all mandatory mods together on client and dedicated server. | Not Started | P0 | 44 | 8 | P0 | Clean client/server boot and no classloading errors. | 0.0.1-dev
2 | P2 | Immersive EGO external subject API | M1 | Consume a stable NPC-facing EGO API with strict MIT/GPL isolation. | Not Started | P0 | 26 | 6 | P1 | Clean client/server boot and no classloading errors. | 0.0.1-dev
3 | P3 | Unified resident kernel | M2 | Create the canonical resident record, host adapters, persistence and repair. | Not Started | P0 | 47 | 8 | P2 | Persistence, repair and adapter tests pass. | 0.0.2-dev
4 | P4 | MineColonies civic bridge | M3 | Use colony, building, housing, job, request, warehouse, permissions and raid systems. | Not Started | P0 | 100 | 10 | P3 | Recruit, assign, request and reload scenario passes. | 0.0.3-dev
5 | P5 | MCA social bridge | M4 | Preserve identity, appearance, personality, relationships, family and age. | Not Started | P0 | 76 | 8 | P4 | No duplicate social graph and family persistence passes. | 0.0.4-dev
6 | P6 | Modern Companions military bridge | M5 | Generalize military roles, orders, equipment, XP, traits, morale and bond. | Not Started | P0 | 87 | 9 | P5 | Order and friendly-fire tests pass. | 0.0.5-dev
7 | P7 | Desert colony vertical slice | M6 | Prove all four pillars in one reproducible dedicated-server scenario. | Not Started | P0 | 97 | 9 | P6 | End-to-end dedicated-server scenario passes. | 0.1.0-alpha
8 | P8 | Unified jobs and professions | M7 | Add profession mapping, skills, schedules, readiness and apprenticeship gates. | Not Started | P1 | 61 | 7 | P7 | No duplication under interruption/restart. | 0.2.0-alpha
9 | P9 | Resource requests and logistics | M7 | Add transaction-safe requests, warehouse access, couriers and reservations. | Not Started | P1 | 73 | 7 | P8 | No duplication under interruption/restart. | 0.2.0-alpha
10 | P10 | NPC work recipes | M8 | Use existing workstations for data-driven resident production. | Not Started | P1 | 71 | 8 | P9 | Recipe, quality and rollback tests pass. | 0.3.0-alpha
11 | P11 | Factions, cultures and reputation | M9 | Add culture, political faction, loyalty, grievances and reputation dimensions. | Not Started | P1 | 81 | 8 | P10 | Bounded economy and explainable reputation pass. | 0.4.0-alpha
12 | P12 | Economy, trade and contracts | M9 | Add scarcity, barter, favor, debt, contracts and optional currency SPI. | Not Started | P1 | 84 | 8 | P11 | Bounded economy and explainable reputation pass. | 0.4.0-alpha
13 | P13 | Defense, raids and command | M10 | Unify guards, militia, patrols, escorts, shelter and raid response. | Not Started | P1 | 79 | 8 | P12 | Combat policy and raid scenario pass. | 0.5.0-alpha
14 | P14 | Households, family and education | M11 | Connect MCA family to homes, care, apprenticeship and migration. | Not Started | P1 | 79 | 8 | P13 | Multi-generation simulation passes. | 0.7.0-beta
15 | P15 | Governance, law, crime and migration | M11 | Add legitimacy, laws, justice, succession and civic movement. | Not Started | P2 | 89 | 8 | P14 | Multi-generation simulation passes. | 0.7.0-beta
16 | P16 | Crises and diplomacy | M12 | Create bounded emergent crisis chains and political relations. | Not Started | P2 | 84 | 8 | P15 | Crisis chains are bounded and recoverable. | 0.8.0-beta
17 | P17 | UI, configuration and performance | M13 | Finish dashboards, TOML profiles, simulation tiers and diagnostics. | Not Started | P2 | 94 | 8 | P16 | Performance budgets and config migrations pass. | 0.9.0-beta
18 | P18 | Hardening and release | M14 | Complete legal, migration, performance, compatibility and release gates. | Not Started | P2 | 84 | 8 | P17 | Reproducible jar/source release and matrix tests pass. | 1.0.0-rc1

## Milestones
Milestone ID | Milestone | Release Target | Status | Goal | Exit Criteria | Owner
M0 | Legal & Source Baseline | Internal Gate | Not Started | Every upstream source and asset boundary is documented. | GPL repo, dependency audit and provenance gates pass. | Codex + Maintainer
M1 | Bootable Integration Harness | 0.0.1-dev | Not Started | All mandatory dependencies boot and EGO API is available. | Clean client/server boot and no classloading errors. | Codex + Maintainer
M2 | Unified Resident Kernel | 0.0.2-dev | Not Started | One civic identity attaches to all supported host families. | Persistence, repair and adapter tests pass. | Codex + Maintainer
M3 | MineColonies Civic Backbone | 0.0.3-dev | Not Started | External residents participate in colony, home, job and logistics. | Recruit, assign, request and reload scenario passes. | Codex + Maintainer
M4 | MCA Social Continuity | 0.0.4-dev | Not Started | MCA family and relationship truth remains intact. | No duplicate social graph and family persistence passes. | Codex + Maintainer
M5 | Unified Military Roles | 0.0.5-dev | Not Started | Supported hosts can follow, guard, patrol, equip and level. | Order and friendly-fire tests pass. | Codex + Maintainer
M6 | Desert Vertical Slice | 0.1.0-alpha | Not Started | All four pillars work together during drought and raid. | End-to-end dedicated-server scenario passes. | Codex + Maintainer
M7 | Production & Logistics Alpha | 0.2.0-alpha | Not Started | Jobs, requests, reservations, couriers and schedules are reliable. | No duplication under interruption/restart. | Codex + Maintainer
M8 | NPC Crafting Alpha | 0.3.0-alpha | Not Started | Residents perform configured work recipes at existing stations. | Recipe, quality and rollback tests pass. | Codex + Maintainer
M9 | Society & Economy Alpha | 0.4.0-alpha | Not Started | Culture, reputation, dynamic value and contracts are playable. | Bounded economy and explainable reputation pass. | Codex + Maintainer
M10 | Defense Alpha | 0.5.0-alpha | Not Started | Military hierarchy, raid response and civilian shelter work. | Combat policy and raid scenario pass. | Codex + Maintainer
M11 | Civic Simulation Beta | 0.7.0-beta | Not Started | Households, education, governance, law and migration persist. | Multi-generation simulation passes. | Codex + Maintainer
M12 | Crisis & Diplomacy Beta | 0.8.0-beta | Not Started | Crises and diplomacy connect survival to politics. | Crisis chains are bounded and recoverable. | Codex + Maintainer
M13 | Performance & UX Beta | 0.9.0-beta | Not Started | Dashboards, configuration and simulation tiers are release quality. | Performance budgets and config migrations pass. | Codex + Maintainer
M14 | Release Candidate | 1.0.0-rc1 | Not Started | Technical, legal, source and documentation gates are complete. | Reproducible jar/source release and matrix tests pass. | Codex + Maintainer

## Backlog
Task ID | Task | Phase | Milestone | Workstream | Type | Priority | Status | Story Points | Depends On | Source Project | License Handling | Deliverable | Acceptance | Codex Execution Note
CIV-001 | Create GPL repository skeleton | P0 | M0 | Governance | Engineering | P0 | Not Started | 3 |  | Original | Original | Create GPL repository skeleton | LICENSE, AGENTS, TASKS and docs exist. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-002 | Audit exact versions and NeoForge intersection | P0 | M0 | Dependencies | Engineering | P0 | Not Started | 8 |  | All | GPL adaptation + provenance | Audit exact versions and NeoForge intersection | One reproducible dependency set is documented. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-003 | Map release artifacts to immutable source commits | P0 | M0 | Legal | Engineering | P0 | Not Started | 8 |  | All | GPL adaptation + provenance | Map release artifacts to immutable source commits | Every mandatory jar maps to source. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-004 | Create THIRD_PARTY_NOTICES and license matrix | P0 | M0 | Legal | Engineering | P0 | Not Started | 5 |  | All | GPL adaptation + provenance | Create THIRD_PARTY_NOTICES and license matrix | Notices distinguish code, assets and trademarks. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-005 | Create code adaptation manifest tooling | P0 | M0 | Tooling | Engineering | P0 | Not Started | 5 |  | All | GPL adaptation + provenance | Create code adaptation manifest tooling | Every copied file is machine-traceable. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-006 | Create forbidden-asset and missing-header CI scans | P0 | M0 | Legal | Engineering | P0 | Not Started | 8 |  | All | GPL adaptation + provenance | Create forbidden-asset and missing-header CI scans | CI blocks unapproved assets and orphaned derivatives. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-007 | Define upstream update/re-audit process | P0 | M0 | Governance | Engineering | P1 | Not Started | 3 |  | All | GPL adaptation + provenance | Define upstream update/re-audit process | Dependency updates trigger compatibility gates. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-008 | Initialize NeoForge 1.21.1 Java 21 project | P1 | M1 | Build | Engineering | P0 | Not Started | 5 |  | Original | Original | Initialize NeoForge 1.21.1 Java 21 project | Project compiles with standard runs. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-009 | Resolve Immersive EGO dependency set | P1 | M1 | Dependencies | Engineering | P0 | Not Started | 5 |  | Immersive EGO | Runtime API only | Resolve Immersive EGO dependency set | EGO and its transitive dependencies resolve. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-010 | Resolve MineColonies and five dependencies | P1 | M1 | Dependencies | Engineering | P0 | Not Started | 8 |  | MineColonies | GPL adaptation + provenance | Resolve MineColonies and five dependencies | All MineColonies runtime dependencies load. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-011 | Resolve MCA Reborn NeoForge dependency | P1 | M1 | Dependencies | Engineering | P0 | Not Started | 5 |  | MCA Reborn | GPL adaptation + provenance | Resolve MCA Reborn NeoForge dependency | MCA source and runtime resolve. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-012 | Resolve Modern Companions artifact/source mismatch | P1 | M1 | Dependencies | Engineering | P0 | Not Started | 8 |  | Modern Companions | GPL adaptation + provenance | Resolve Modern Companions artifact/source mismatch | Runtime jar maps to verified source commit. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-013 | Create client smoke run | P1 | M1 | Testing | Engineering | P0 | Not Started | 3 |  | All | GPL adaptation + provenance | Create client smoke run | Client reaches title screen. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-014 | Create dedicated-server smoke run | P1 | M1 | Testing | Engineering | P0 | Not Started | 5 |  | All | GPL adaptation + provenance | Create dedicated-server smoke run | Server starts without client-only classloading. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-015 | Create CI build/test/provenance workflow | P1 | M1 | CI | Engineering | P1 | Not Started | 5 |  | Original | Original | Create CI build/test/provenance workflow | Build and governance checks run automatically. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-016 | Document required EgoSubject API | P2 | M1 | API | Engineering | P0 | Not Started | 5 |  | Immersive EGO | Runtime API only | Document required EgoSubject API | Neutral NPC API contract is explicit. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-017 | Verify external subject registration and snapshots | P2 | M1 | API | Engineering | P0 | Not Started | 5 |  | Immersive EGO | Runtime API only | Verify external subject registration and snapshots | CIVITAS can resolve supported NPCs. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-018 | Implement CivitasEgoFacade | P2 | M1 | API | Engineering | P0 | Not Started | 5 |  | Original | Original | Implement CivitasEgoFacade | All EGO calls are isolated. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-019 | Implement bounded EGO snapshot cache | P2 | M1 | Performance | Engineering | P1 | Not Started | 5 |  | Original | Original | Implement bounded EGO snapshot cache | Work/combat avoids hot repeated calls. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-020 | Implement minimum-version diagnostics | P2 | M1 | Diagnostics | Engineering | P1 | Not Started | 3 |  | Original | Original | Implement minimum-version diagnostics | Missing API fails clearly. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-021 | Create MIT/GPL boundary scan | P2 | M1 | Legal | Engineering | P0 | Not Started | 3 |  | Original | Original | Create MIT/GPL boundary scan | No CIVITAS GPL package enters EGO repository. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-022 | Define UnifiedResidentRecord and codec | P3 | M2 | Resident | Engineering | P0 | Not Started | 8 |  | Original | Original | Define UnifiedResidentRecord and codec | Record serializes and validates. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-023 | Define ResidentHostAdapter interface | P3 | M2 | Resident | Engineering | P0 | Not Started | 5 |  | Original | Original | Define ResidentHostAdapter interface | Hosts share a stable contract. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-024 | Implement host detection and priority | P3 | M2 | Resident | Engineering | P0 | Not Started | 5 |  | Original | Original | Implement host detection and priority | Exactly one primary adapter is chosen. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-025 | Implement UUID/external-ID repair | P3 | M2 | Resident | Engineering | P0 | Not Started | 8 |  | Original | Original | Implement UUID/external-ID repair | Stale and duplicate links repair safely. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-026 | Implement resident SavedData index | P3 | M2 | Persistence | Engineering | P0 | Not Started | 8 |  | Original | Original | Implement resident SavedData index | Unloaded residents remain resolvable. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-027 | Implement host attachment reference | P3 | M2 | Persistence | Engineering | P0 | Not Started | 5 |  | Original | Original | Implement host attachment reference | Loaded hosts point to canonical record. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-028 | Implement simulation tiers | P3 | M2 | Performance | Engineering | P1 | Not Started | 5 |  | Original | Original | Implement simulation tiers | Near/far/unloaded/aggregate tiers are deterministic. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-029 | Implement resident dossier debug command | P3 | M2 | Diagnostics | Engineering | P1 | Not Started | 3 |  | Original | Original | Implement resident dossier debug command | Authorities and links are inspectable. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-030 | Audit MineColonies civic and worker packages | P4 | M3 | MineColonies | Engineering | P0 | Not Started | 13 |  | MineColonies | GPL adaptation + provenance | Audit MineColonies civic and worker packages | Direct-use vs adaptation map exists. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-031 | Implement version-pinned ColonyFacade | P4 | M3 | MineColonies | Engineering | P0 | Not Started | 8 |  | MineColonies | GPL adaptation + provenance | Implement version-pinned ColonyFacade | Colony lookup and membership are isolated. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-032 | Implement BuildingAssignmentFacade | P4 | M3 | MineColonies | Engineering | P0 | Not Started | 8 |  | MineColonies | GPL adaptation + provenance | Implement BuildingAssignmentFacade | External residents can hold valid jobs. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-033 | Implement family-aware housing adapter | P4 | M3 | MineColonies | Engineering | P0 | Not Started | 8 |  | MineColonies | GPL adaptation + provenance | Implement family-aware housing adapter | Housing respects MCA household constraints. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-034 | Implement ExternalCitizenProxy | P4 | M3 | MineColonies | Engineering | P0 | Not Started | 13 |  | MineColonies | GPL adaptation + provenance | Implement ExternalCitizenProxy | MCA hosts work without entity replacement. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-035 | Implement WorkOrderFacade | P4 | M3 | MineColonies | Engineering | P1 | Not Started | 8 |  | MineColonies | GPL adaptation + provenance | Implement WorkOrderFacade | General workers consume relevant work orders. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-036 | Implement RequestSystemFacade | P4 | M3 | MineColonies | Engineering | P0 | Not Started | 13 |  | MineColonies | GPL adaptation + provenance | Implement RequestSystemFacade | Requests create, fulfill and cancel safely. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-037 | Implement WarehouseQueryFacade | P4 | M3 | MineColonies | Engineering | P0 | Not Started | 13 |  | MineColonies | GPL adaptation + provenance | Implement WarehouseQueryFacade | Stock access is transaction-safe. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-038 | Implement colony permissions/events adapter | P4 | M3 | MineColonies | Engineering | P1 | Not Started | 8 |  | MineColonies | GPL adaptation + provenance | Implement colony permissions/events adapter | Lifecycle and authority are respected. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-039 | Implement raid/guard signal adapter | P4 | M3 | MineColonies | Engineering | P1 | Not Started | 8 |  | MineColonies | GPL adaptation + provenance | Implement raid/guard signal adapter | Threat state drives unified orders. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-040 | Audit MCA identity/social/family packages | P5 | M4 | MCA | Engineering | P0 | Not Started | 13 |  | MCA Reborn | GPL adaptation + provenance | Audit MCA identity/social/family packages | Authoritative data and hooks are mapped. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-041 | Implement McaResidentHostAdapter | P5 | M4 | MCA | Engineering | P0 | Not Started | 8 |  | MCA Reborn | GPL adaptation + provenance | Implement McaResidentHostAdapter | MCA host attaches non-destructively. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-042 | Implement relationship facade | P5 | M4 | MCA | Engineering | P0 | Not Started | 8 |  | MCA Reborn | GPL adaptation + provenance | Implement relationship facade | MCA remains relationship authority. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-043 | Implement family graph facade | P5 | M4 | MCA | Engineering | P0 | Not Started | 13 |  | MCA Reborn | GPL adaptation + provenance | Implement family graph facade | Family truth is never duplicated. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-044 | Implement personality and mood bridge | P5 | M4 | MCA | Engineering | P1 | Not Started | 8 |  | MCA Reborn | GPL adaptation + provenance | Implement personality and mood bridge | Traits influence decisions via normalized signals. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-045 | Implement age and life-stage bridge | P5 | M4 | MCA | Engineering | P1 | Not Started | 8 |  | MCA Reborn | GPL adaptation + provenance | Implement age and life-stage bridge | Capabilities follow age safely. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-046 | Implement recruitment/dialogue actions | P5 | M4 | MCA | Engineering | P0 | Not Started | 13 |  | MCA Reborn | GPL adaptation + provenance | Implement recruitment/dialogue actions | Civic choices use MCA interaction flow. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-047 | Implement gift/economy event bridge | P5 | M4 | MCA | Engineering | P2 | Not Started | 5 |  | MCA Reborn | GPL adaptation + provenance | Implement gift/economy event bridge | Gifts score once across systems. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-048 | Audit Modern Companions code and placeholders | P6 | M5 | Companions | Engineering | P0 | Not Started | 13 |  | Modern Companions | GPL adaptation + provenance | Audit Modern Companions code and placeholders | Only stable eligible systems are mapped. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-049 | Resolve Human Companions/Basic Weapons lineage | P6 | M5 | Legal | Engineering | P0 | Not Started | 8 |  | Modern Companions | GPL adaptation + provenance | Resolve Human Companions/Basic Weapons lineage | Affected code has verified license chain. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-050 | Implement host-neutral MilitaryRole model | P6 | M5 | Combat | Engineering | P0 | Not Started | 8 |  | Modern Companions | GPL adaptation + provenance | Implement host-neutral MilitaryRole model | Roles are data-driven. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-051 | Implement unified order state machine | P6 | M5 | Combat | Engineering | P0 | Not Started | 13 |  | Modern Companions | GPL adaptation + provenance | Implement unified order state machine | Follow/guard/patrol/escort/retreat work. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-052 | Implement equipment evaluation adapter | P6 | M5 | Combat | Engineering | P0 | Not Started | 13 |  | Modern Companions | GPL adaptation + provenance | Implement equipment evaluation adapter | Best valid gear is selected safely. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-053 | Implement combat XP/level bridge | P6 | M5 | Combat | Engineering | P1 | Not Started | 8 |  | Modern Companions | GPL adaptation + provenance | Implement combat XP/level bridge | Progress persists in resident record. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-054 | Implement traits, morale and bond bridge | P6 | M5 | Combat | Engineering | P1 | Not Started | 8 |  | Modern Companions | GPL adaptation + provenance | Implement traits, morale and bond bridge | No duplication with MCA personality. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-055 | Implement safe recall policy | P6 | M5 | Combat | Engineering | P1 | Not Started | 8 |  | Modern Companions | GPL adaptation + provenance | Implement safe recall policy | Recall is permission and dimension safe. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-056 | Implement faction/family friendly-fire policy | P6 | M5 | Combat | Engineering | P0 | Not Started | 8 |  | Modern Companions | GPL adaptation + provenance | Implement faction/family friendly-fire policy | Protected targets are never selected. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-057 | Create desert integration fixture | P7 | M6 | Vertical Slice | Engineering | P0 | Not Started | 8 |  | All | GPL adaptation + provenance | Create desert integration fixture | Reproducible test settlement exists. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-058 | Recruit MCA villager into MineColonies colony | P7 | M6 | Vertical Slice | Engineering | P0 | Not Started | 13 |  | All | GPL adaptation + provenance | Recruit MCA villager into MineColonies colony | One resident record; MCA identity preserved. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-059 | Assign family-aware housing and profession | P7 | M6 | Vertical Slice | Engineering | P0 | Not Started | 13 |  | All | GPL adaptation + provenance | Assign family-aware housing and profession | Home/building/job are valid. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-060 | Connect EGO readiness to work schedule | P7 | M6 | Vertical Slice | Engineering | P0 | Not Started | 13 |  | Immersive EGO | Runtime API only | Connect EGO readiness to work schedule | Drought alters readiness and production. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-061 | Fulfill warehouse-backed resource request | P7 | M6 | Vertical Slice | Engineering | P0 | Not Started | 13 |  | MineColonies | GPL adaptation + provenance | Fulfill warehouse-backed resource request | Exactly one transfer occurs. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-062 | Assign guard role and patrol | P7 | M6 | Vertical Slice | Engineering | P0 | Not Started | 13 |  | Modern Companions | GPL adaptation + provenance | Assign guard role and patrol | Resident protects civilians. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-063 | Preserve family/relationship across reload | P7 | M6 | Vertical Slice | Engineering | P0 | Not Started | 8 |  | MCA Reborn | GPL adaptation + provenance | Preserve family/relationship across reload | MCA social state survives restart. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-064 | Generate reputation and migration effects | P7 | M6 | Vertical Slice | Engineering | P1 | Not Started | 8 |  | Original | Original | Generate reputation and migration effects | Player response changes civic outcomes. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-065 | Run dedicated-server scenario | P7 | M6 | Vertical Slice | Engineering | P0 | Not Started | 8 |  | All | GPL adaptation + provenance | Run dedicated-server scenario | Full slice passes server smoke test. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-066 | Define profession/specialization registry | P8 | M7 | Jobs | Engineering | P0 | Not Started | 8 |  | Original | Original | Define profession/specialization registry | Mappings are data-driven. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-067 | Implement skills and experience | P8 | M7 | Jobs | Engineering | P1 | Not Started | 8 |  | MineColonies | GPL adaptation + provenance | Implement skills and experience | Skills progress from work. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-068 | Implement EGO work readiness | P8 | M7 | Jobs | Engineering | P0 | Not Started | 8 |  | Immersive EGO | Runtime API only | Implement EGO work readiness | Needs affect work deterministically. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-069 | Implement schedule planner | P8 | M7 | Jobs | Engineering | P1 | Not Started | 13 |  | Original | Original | Implement schedule planner | Work, sleep, meals and family coordinate. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-070 | Implement building/job mapping profiles | P8 | M7 | Jobs | Engineering | P0 | Not Started | 8 |  | MineColonies | GPL adaptation + provenance | Implement building/job mapping profiles | MineColonies roles map cleanly. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-071 | Implement progressive refusal/recovery | P8 | M7 | Jobs | Engineering | P1 | Not Started | 8 |  | Original | Original | Implement progressive refusal/recovery | Failure escalates gradually. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-072 | Implement qualification/apprenticeship gates | P8 | M7 | Jobs | Engineering | P2 | Not Started | 8 |  | Original | Original | Implement qualification/apprenticeship gates | Workers learn before mastery. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-073 | Define atomic transaction model | P9 | M7 | Logistics | Engineering | P0 | Not Started | 13 |  | MineColonies | GPL adaptation + provenance | Define atomic transaction model | Inputs/outputs have explicit lifecycle. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-074 | Implement item-source resolver | P9 | M7 | Logistics | Engineering | P0 | Not Started | 8 |  | MineColonies | GPL adaptation + provenance | Implement item-source resolver | Worker/building/warehouse sources follow policy. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-075 | Implement reservation ledger | P9 | M7 | Logistics | Engineering | P0 | Not Started | 13 |  | MineColonies | GPL adaptation + provenance | Implement reservation ledger | Stacks cannot be double-reserved. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-076 | Implement courier handoff | P9 | M7 | Logistics | Engineering | P1 | Not Started | 13 |  | MineColonies | GPL adaptation + provenance | Implement courier handoff | Requests use MineColonies flow when appropriate. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-077 | Implement cancellation and rollback | P9 | M7 | Logistics | Engineering | P0 | Not Started | 13 |  | Original | Original | Implement cancellation and rollback | Interruptions do not duplicate. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-078 | Implement restart repair | P9 | M7 | Logistics | Engineering | P0 | Not Started | 8 |  | Original | Original | Implement restart repair | Stale transactions recover. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-079 | Implement request diagnostics | P9 | M7 | Diagnostics | Engineering | P1 | Not Started | 5 |  | Original | Original | Implement request diagnostics | Transactions are explainable. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-080 | Define NPC work recipe codec | P10 | M8 | Work Recipes | Engineering | P0 | Not Started | 13 |  | Original | Original | Define NPC work recipe codec | Recipes model worker, station, inputs and outputs. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-081 | Implement workstation tag resolver | P10 | M8 | Work Recipes | Engineering | P0 | Not Started | 8 |  | Original | Original | Implement workstation tag resolver | Existing stations are data-driven. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-082 | Implement worker-state conditions | P10 | M8 | Work Recipes | Engineering | P0 | Not Started | 8 |  | Original | Original | Implement worker-state conditions | Readiness, skill and safety gate work. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-083 | Implement multi-stage execution | P10 | M8 | Work Recipes | Engineering | P1 | Not Started | 13 |  | MineColonies | GPL adaptation + provenance | Implement multi-stage execution | Stages are deterministic. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-084 | Implement quality/failure model | P10 | M8 | Work Recipes | Engineering | P2 | Not Started | 8 |  | Original | Original | Implement quality/failure model | Quality is bounded and explainable. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-085 | Implement recipe validation | P10 | M8 | Work Recipes | Engineering | P0 | Not Started | 8 |  | Original | Original | Implement recipe validation | Invalid data disables safely. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-086 | Add machine-replacement policy tags | P10 | M8 | Work Recipes | Engineering | P1 | Not Started | 5 |  | Original | Original | Add machine-replacement policy tags | Packmakers control replacement scope. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-087 | Add vanilla-station examples | P10 | M8 | Work Recipes | Engineering | P1 | Not Started | 8 |  | Original | Original | Add vanilla-station examples | Examples add no new content. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-088 | Define faction/culture/settlement models | P11 | M9 | Society | Engineering | P0 | Not Started | 13 |  | Original | Original | Define faction/culture/settlement models | Identity concepts remain distinct. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-089 | Implement biome culture seeding | P11 | M9 | Culture | Engineering | P1 | Not Started | 8 |  | Immersive EGO | Runtime API only | Implement biome culture seeding | Biome/population seed culture. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-090 | Implement cultural practices | P11 | M9 | Culture | Engineering | P1 | Not Started | 13 |  | Original | Original | Implement cultural practices | Schedules, food, trade and defense adapt. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-091 | Implement multidimensional reputation | P11 | M9 | Reputation | Engineering | P0 | Not Started | 13 |  | Original | Original | Implement multidimensional reputation | Trust/respect/fear/honor/crime/favor/debt persist. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-092 | Implement loyalty and grievances | P11 | M9 | Reputation | Engineering | P1 | Not Started | 8 |  | Original | Original | Implement loyalty and grievances | Residents remember treatment. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-093 | Implement faction relation graph | P11 | M9 | Faction | Engineering | P1 | Not Started | 13 |  | Original | Original | Implement faction relation graph | Relations are bounded and explicit. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-094 | Implement reputation event bus | P11 | M9 | Reputation | Engineering | P0 | Not Started | 8 |  | Original | Original | Implement reputation event bus | Events score once. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-095 | Implement reputation explain command | P11 | M9 | Diagnostics | Engineering | P1 | Not Started | 5 |  | Original | Original | Implement reputation explain command | Causes and decay are visible. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-096 | Define goods/services value model | P12 | M9 | Economy | Engineering | P0 | Not Started | 13 |  | Original | Original | Define goods/services value model | Value responds to stock and context. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-097 | Implement scarcity from colony stock | P12 | M9 | Economy | Engineering | P0 | Not Started | 13 |  | MineColonies | GPL adaptation + provenance | Implement scarcity from colony stock | Warehouse drives bounded prices. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-098 | Implement barter offers | P12 | M9 | Trade | Engineering | P1 | Not Started | 8 |  | Original | Original | Implement barter offers | Trades can avoid emeralds. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-099 | Implement favor/debt ledger | P12 | M9 | Economy | Engineering | P0 | Not Started | 8 |  | Original | Original | Implement favor/debt ledger | Obligations persist. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-100 | Implement contracts model | P12 | M9 | Contracts | Engineering | P1 | Not Started | 13 |  | Original | Original | Implement contracts model | Issuer/objective/reward/deadline persist. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-101 | Deliver contracts through MCA dialogue | P12 | M9 | Contracts | Engineering | P1 | Not Started | 13 |  | MCA Reborn | GPL adaptation + provenance | Deliver contracts through MCA dialogue | Residents present civic work. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-102 | Implement anti-inflation controls | P12 | M9 | Economy | Engineering | P0 | Not Started | 8 |  | Original | Original | Implement anti-inflation controls | Loops remain bounded. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-103 | Implement optional currency SPI | P12 | M9 | Economy | Engineering | P2 | Not Started | 8 |  | Original | Original | Implement optional currency SPI | Future currency mods can integrate. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-104 | Define military hierarchy | P13 | M10 | Defense | Engineering | P1 | Not Started | 8 |  | Original | Original | Define military hierarchy | Civilian/militia/guard/specialist/commander exist. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-105 | Map MineColonies guard buildings | P13 | M10 | Defense | Engineering | P0 | Not Started | 13 |  | MineColonies | GPL adaptation + provenance | Map MineColonies guard buildings | Guard jobs assign host-neutral roles. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-106 | Implement civilian shelter order | P13 | M10 | Defense | Engineering | P0 | Not Started | 8 |  | Original | Original | Implement civilian shelter order | Civilians seek valid safety. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-107 | Implement protect-family priority | P13 | M10 | Defense | Engineering | P1 | Not Started | 8 |  | MCA Reborn | GPL adaptation + provenance | Implement protect-family priority | Family affects defense without loops. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-108 | Implement raid response coordinator | P13 | M10 | Defense | Engineering | P0 | Not Started | 13 |  | MineColonies | GPL adaptation + provenance | Implement raid response coordinator | Raid state creates coherent orders. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-109 | Implement escort/caravan defense | P13 | M10 | Defense | Engineering | P1 | Not Started | 13 |  | Modern Companions | GPL adaptation + provenance | Implement escort/caravan defense | Workers and families can be protected. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-110 | Implement casualty/trauma consequences | P13 | M10 | Defense | Engineering | P1 | Not Started | 8 |  | Immersive EGO | Runtime API only | Implement casualty/trauma consequences | EGO and morale reflect battle. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-111 | Implement command permissions | P13 | M10 | Defense | Engineering | P0 | Not Started | 8 |  | Original | Original | Implement command permissions | Authority and colony permissions gate orders. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-112 | Define household and shared-home policy | P14 | M11 | Household | Engineering | P0 | Not Started | 13 |  | MCA Reborn | GPL adaptation + provenance | Define household and shared-home policy | MCA family maps to housing. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-113 | Implement household inventory policy | P14 | M11 | Household | Engineering | P1 | Not Started | 8 |  | Original | Original | Implement household inventory policy | Shared essentials respect reservations. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-114 | Implement care responsibilities | P14 | M11 | Family | Engineering | P1 | Not Started | 8 |  | Original | Original | Implement care responsibilities | Children/injured residents receive support. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-115 | Implement child safety gates | P14 | M11 | Family | Engineering | P0 | Not Started | 8 |  | MCA Reborn | GPL adaptation + provenance | Implement child safety gates | Unsafe jobs and combat are denied. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-116 | Implement apprenticeship | P14 | M11 | Education | Engineering | P1 | Not Started | 13 |  | MineColonies | GPL adaptation + provenance | Implement apprenticeship | Qualified adults teach youth. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-117 | Implement adulthood profession transition | P14 | M11 | Education | Engineering | P1 | Not Started | 8 |  | MCA Reborn | GPL adaptation + provenance | Implement adulthood profession transition | Life stage unlocks work safely. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-118 | Implement household migration | P14 | M11 | Migration | Engineering | P1 | Not Started | 13 |  | Original | Original | Implement household migration | Families move together by default. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-119 | Separate culture and biological origin inheritance | P14 | M11 | Family | Engineering | P2 | Not Started | 8 |  | Immersive EGO | Runtime API only | Separate culture and biological origin inheritance | Concepts never collapse together. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-120 | Define governance and offices | P15 | M11 | Governance | Engineering | P1 | Not Started | 13 |  | Original | Original | Define governance and offices | Leader/council/guild roles are data-driven. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-121 | Implement legitimacy | P15 | M11 | Governance | Engineering | P0 | Not Started | 8 |  | Original | Original | Implement legitimacy | Security/prosperity/trust/law influence authority. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-122 | Implement configurable laws | P15 | M11 | Law | Engineering | P1 | Not Started | 13 |  | Original | Original | Implement configurable laws | Actions/jurisdiction/consequences are profiles. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-123 | Implement crime ledger | P15 | M11 | Crime | Engineering | P0 | Not Started | 13 |  | Original | Original | Implement crime ledger | Theft/assault/sabotage record once. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-124 | Implement justice responses | P15 | M11 | Crime | Engineering | P1 | Not Started | 13 |  | Original | Original | Implement justice responses | Warnings/fines/exile/hostility are configurable. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-125 | Implement migration pressure | P15 | M11 | Migration | Engineering | P0 | Not Started | 8 |  | Original | Original | Implement migration pressure | Housing/food/safety/family drive movement. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-126 | Implement succession hooks | P15 | M11 | Governance | Engineering | P2 | Not Started | 13 |  | MCA Reborn | GPL adaptation + provenance | Implement succession hooks | Leadership loss is safe. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-127 | Create governance diagnostics | P15 | M11 | UI | Engineering | P2 | Not Started | 8 |  | Original | Original | Create governance diagnostics | Civic state is explainable. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-128 | Define crisis engine and stages | P16 | M12 | Crises | Engineering | P0 | Not Started | 13 |  | Original | Original | Define crisis engine and stages | Trigger/escalation/intervention/recovery exist. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-129 | Implement drought crisis | P16 | M12 | Crises | Engineering | P0 | Not Started | 8 |  | Immersive EGO | Runtime API only | Implement drought crisis | Water shortage propagates through systems. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-130 | Implement famine crisis | P16 | M12 | Crises | Engineering | P0 | Not Started | 8 |  | MineColonies | GPL adaptation + provenance | Implement famine crisis | Food shortage affects loyalty/trade. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-131 | Implement labor shortage/strike | P16 | M12 | Crises | Engineering | P1 | Not Started | 13 |  | Original | Original | Implement labor shortage/strike | Overwork can reduce labor. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-132 | Implement raid trauma/exhaustion | P16 | M12 | Crises | Engineering | P1 | Not Started | 8 |  | All | GPL adaptation + provenance | Implement raid trauma/exhaustion | Repeated attacks degrade recovery. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-133 | Implement succession crisis | P16 | M12 | Crises | Engineering | P2 | Not Started | 13 |  | Original | Original | Implement succession crisis | Leadership loss divides support. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-134 | Implement diplomacy/treaties | P16 | M12 | Diplomacy | Engineering | P2 | Not Started | 13 |  | Original | Original | Implement diplomacy/treaties | Trade/alliance/truce/passage persist. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-135 | Implement crisis diagnostics/admin controls | P16 | M12 | Diagnostics | Engineering | P1 | Not Started | 8 |  | Original | Original | Implement crisis diagnostics/admin controls | Escalation is traceable and reversible. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-136 | Create resident dossier UI | P17 | M13 | UI | Engineering | P1 | Not Started | 13 |  | BlockUI | Runtime API only | Create resident dossier UI | Identity, EGO, work, family and orders display. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-137 | Create settlement dashboard | P17 | M13 | UI | Engineering | P1 | Not Started | 13 |  | BlockUI | Runtime API only | Create settlement dashboard | Population/stock/work/security/crises display. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-138 | Create faction ledger UI | P17 | M13 | UI | Engineering | P2 | Not Started | 13 |  | BlockUI | Runtime API only | Create faction ledger UI | Relations/laws/reputation display. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-139 | Implement exhaustive ModConfigSpec | P17 | M13 | Configuration | Engineering | P0 | Not Started | 13 |  | Original | Original | Implement exhaustive ModConfigSpec | Material gameplay rules are configurable. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-140 | Implement dynamic TOML loaders | P17 | M13 | Configuration | Engineering | P0 | Not Started | 13 |  | Original | Original | Implement dynamic TOML loaders | Profiles validate atomically. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-141 | Implement simulation budgets | P17 | M13 | Performance | Engineering | P0 | Not Started | 13 |  | Original | Original | Implement simulation budgets | AI and pathfinding costs are bounded. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-142 | Implement profiling commands | P17 | M13 | Performance | Engineering | P1 | Not Started | 8 |  | Original | Original | Implement profiling commands | Tick/cache/transaction metrics are visible. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-143 | Implement config migration/fallback | P17 | M13 | Configuration | Engineering | P0 | Not Started | 8 |  | Original | Original | Implement config migration/fallback | Bad config does not corrupt worlds. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-144 | Run dedicated-server soak test | P18 | M14 | Release | Engineering | P0 | Not Started | 13 |  | All | GPL adaptation + provenance | Run dedicated-server soak test | No leaks, dupes or classload errors. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-145 | Run multi-colony/migration tests | P18 | M14 | Release | Engineering | P0 | Not Started | 13 |  | All | GPL adaptation + provenance | Run multi-colony/migration tests | Cross-colony state is consistent. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-146 | Run transaction stress tests | P18 | M14 | Release | Engineering | P0 | Not Started | 13 |  | All | GPL adaptation + provenance | Run transaction stress tests | Interruptions never duplicate. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-147 | Run compatibility matrix | P18 | M14 | Release | Engineering | P0 | Not Started | 8 |  | All | GPL adaptation + provenance | Run compatibility matrix | Supported combinations are documented. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-148 | Complete provenance manifest | P18 | M14 | Legal | Engineering | P0 | Not Started | 13 |  | All | GPL adaptation + provenance | Complete provenance manifest | Every adapted file is traceable. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-149 | Complete asset/trademark audit | P18 | M14 | Legal | Engineering | P0 | Not Started | 8 |  | All | GPL adaptation + provenance | Complete asset/trademark audit | No restricted asset or affiliation claim remains. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-150 | Generate reproducible jar/source release | P18 | M14 | Release | Engineering | P0 | Not Started | 8 |  | Original | Original | Generate reproducible jar/source release | Binary and source match. | Inspect pinned upstream source first; update provenance; build and test before completion.
CIV-151 | Complete docs/credits/upgrade guide | P18 | M14 | Documentation | Engineering | P1 | Not Started | 8 |  | Original | Original | Complete docs/credits/upgrade guide | Release is installable and maintainable. | Inspect pinned upstream source first; update provenance; build and test before completion.

## Risks
Risk ID | Risk | Category | Impact | Likelihood | Mitigation | Owning Phase | Status | Owner
R-001 | MineColonies internal API instability | Technical | Critical | Likely | Exact pinning, facades and integration tests. | P0 | Open | Codex + Maintainer
R-002 | Modern Companions source/artifact mismatch | Legal/Technical | Critical | Likely | Map jar to commit before adapting. | P0 | Open | Codex + Maintainer
R-003 | Third-party code lineage ambiguity | Legal | Critical | Possible | Block adaptation until verified. | P0 | Open | Codex + Maintainer
R-004 | Duplicate resident identity | Data | Critical | Possible | Canonical ID, repair scanner and one-host rule. | P3 | Open | Codex + Maintainer
R-005 | Duplicate MCA family graph | Data | High | Possible | MCA remains authoritative. | P5 | Open | Codex + Maintainer
R-006 | Citizen-specific MineColonies code blocks MCA hosts | Architecture | Critical | Likely | External proxy plus generalized worker runtime. | P4 | Open | Codex + Maintainer
R-007 | Competing AI goals | AI | Critical | Likely | Central order arbitration. | P6 | Open | Codex + Maintainer
R-008 | Item duplication in requests | Economy | Critical | Possible | Atomic reservations, rollback and restart repair. | P9 | Open | Codex + Maintainer
R-009 | Pathfinding/TPS degradation | Performance | High | Likely | Budgets, caches and simulation tiers. | P17 | Open | Codex + Maintainer
R-010 | Client classloading on server | Compatibility | Critical | Possible | Dist separation and server CI. | P1 | Open | Codex + Maintainer
R-011 | Dependency update breaks internals | Compatibility | High | Likely | Exact support matrix and explicit rejection. | P18 | Open | Codex + Maintainer
R-012 | GPL leakage into Immersive EGO | Legal | Critical | Possible | Separate repos and CI package scan. | P2 | Open | Codex + Maintainer
R-013 | Restricted assets copied | Legal | Critical | Possible | Hash/namespace scanner and original assets. | P0 | Open | Codex + Maintainer
R-014 | Housing/family conflict | Gameplay | High | Possible | Joint transactional assignment. | P14 | Open | Codex + Maintainer
R-015 | Children assigned unsafe roles | Safety | High | Possible | Life-stage gates. | P14 | Open | Codex + Maintainer
R-016 | Raid targets family/allies | Combat | Critical | Possible | Unified target policy tests. | P13 | Open | Codex + Maintainer
R-017 | Infinite-value economy loops | Economy | High | Likely | Caps, cooldowns and self-trade detection. | P12 | Open | Codex + Maintainer
R-018 | Runaway crisis feedback | Simulation | High | Possible | Stages, caps and interventions. | P16 | Open | Codex + Maintainer
R-019 | Configuration overload | UX | Medium | Likely | Presets, validation and generated docs. | P17 | Open | Codex + Maintainer
R-020 | BlockUI incompatibility | UI | Medium | Possible | Pinned version and fallback diagnostics. | P17 | Open | Codex + Maintainer
R-021 | Save migration corrupts colony | Data | Critical | Possible | Backups, dry run and rollback. | P18 | Open | Codex + Maintainer
R-022 | Unloaded residents duplicate work | Simulation | High | Possible | Idempotent abstract advancement. | P17 | Open | Codex + Maintainer
R-023 | EGO NPC API unavailable | Dependency | Critical | Possible | Explicit prerequisite and fail-fast. | P2 | Open | Codex + Maintainer
R-024 | Unauthorized resident commands | Security | High | Possible | MineColonies permissions plus CIVITAS authority. | P13 | Open | Codex + Maintainer
R-025 | Scope becomes unfinishable | Delivery | High | Likely | Vertical-slice gate and phase exits. | P7 | Open | Codex + Maintainer

## Dependencies
Dependency | Required | Role | Baseline | License | Runtime Packaging | Source URL | Audit Status
Minecraft | Yes | Game runtime | 1.21.1 | Commercial EULA | External | https://www.minecraft.net/ | Pin
Java | Yes | JVM | 21 | OpenJDK distribution dependent | External | https://openjdk.org/projects/jdk/21/ | Pin
NeoForge | Yes | Loader/API | Resolve compatible 21.1.x intersection | LGPL-2.1-only | External | https://github.com/neoforged/NeoForge | Audit
Immersive EGO | Yes | Physiology/psychology API | 0.1.0-alpha.1 API target | MIT | External | Project repository | Prerequisite
MineColonies | Yes | Colony/jobs/logistics/raids | 1.1.1319 stable planning baseline | GPL-3.0 | External + selected adaptation | https://github.com/ldtteam/minecolonies/tree/version/1.21 | Audit
BlockUI | Via MineColonies | UI framework | Exact compatible build | Audit exact version | External | https://github.com/ldtteam/BlockUI | Audit
Domum Ornamentum | Via MineColonies | Content dependency | Exact compatible build | Audit exact version | External | https://github.com/ldtteam/Domum-Ornamentum | Audit
Multi-Piston | Via MineColonies | Utility dependency | Exact compatible build | Audit exact version | External | https://github.com/ldtteam/multipiston | Audit
Structurize | Via MineColonies | Structure framework | Exact compatible build | Audit exact version | External | https://github.com/ldtteam/Structurize | Audit
TownTalk | Via MineColonies | Citizen speech | Exact compatible build | Audit exact version | External | https://github.com/ldtteam/TownTalk | Audit
MCA Reborn | Yes | Identity/family/relationships/dialogue | 7.7.11 NeoForge 1.21.1 | GPL-3.0-only | External + selected adaptation | https://github.com/Luke100000/minecraft-comes-alive/tree/1.21.1 | Audit
Modern Companions | Yes | Military roles/orders/equipment/XP | CurseForge 2.0; source mapping unresolved | GPL-3.0-only | External + selected adaptation | https://github.com/STRHercules/ModernCompanions | Critical audit
Apothic Attributes | Transitive | Attribute display | Pinned by Immersive EGO | MIT code; assets separate | External | https://github.com/Shadows-of-Fire/Apothic-Attributes | Inherited
Placebo | Transitive | Apothic library | Pinned by Immersive EGO | MIT | External | https://github.com/Shadows-of-Fire/Placebo | Inherited
MariesLib | Transitive | EGO value tracking | Pinned by Immersive EGO | LGPL-3.0-only | External | https://github.com/kgbcupcake/MarieLib | Inherited
Lightman's Currency | No | Future currency SPI | Deferred | Apache-2.0 | External optional | https://github.com/Lightman314/LightmansCurrency | Deferred

## Tests
Test ID | Phase | Category | Test | Automation | Priority | Status | Expected
T-001 | P1 | Build | All mandatory dependencies resolve from clean cache. | CI | P0 | Not Started | Build resolves reproducibly.
T-002 | P1 | Server | Dedicated server starts with all mandatory mods. | Smoke | P0 | Not Started | No client classloading.
T-003 | P3 | Persistence | UnifiedResidentRecord save/load round-trip. | JUnit/GameTest | P0 | Not Started | Identifiers and schema persist.
T-004 | P3 | Repair | Duplicate host links repair safely. | JUnit | P0 | Not Started | One canonical resident remains.
T-005 | P4 | MineColonies | MCA host joins colony without conversion. | GameTest | P0 | Not Started | Identity and membership remain valid.
T-006 | P4 | Housing | Family-aware home assignment rolls back on conflict. | GameTest | P0 | Not Started | No orphaned assignment.
T-007 | P4 | Requests | External worker fulfills one request. | GameTest | P0 | Not Started | Exactly one transfer.
T-008 | P5 | MCA | Family graph remains MCA-authoritative. | Integration | P0 | Not Started | No duplicate graph.
T-009 | P6 | Combat | MCA host executes guard/patrol. | GameTest | P0 | Not Started | Order persists and targets safely.
T-010 | P6 | Friendly Fire | Family/colony/allies are protected. | GameTest | P0 | Not Started | No protected target selected.
T-011 | P7 | Vertical Slice | Drought reduces readiness and production. | Scenario | P0 | Not Started | EGO causes explainable change.
T-012 | P9 | Duplication | Worker dies after reservation. | GameTest | P0 | Not Started | No duplicate or untracked loss.
T-013 | P9 | Restart | Server restarts during transaction. | Integration | P0 | Not Started | Ledger repairs deterministically.
T-014 | P10 | Recipe | Invalid work recipe is rejected safely. | JUnit | P0 | Not Started | Precise validation error.
T-015 | P11 | Reputation | One event contributes once. | JUnit | P0 | Not Started | No double counting.
T-016 | P12 | Economy | Self-trade cannot create infinite value. | Simulation | P0 | Not Started | Net value bounded.
T-017 | P13 | Raid | Raid triggers defense and shelter. | Scenario | P0 | Not Started | Guards defend; civilians shelter.
T-018 | P14 | Children | Child cannot receive unsafe role. | JUnit/GameTest | P0 | Not Started | Assignment rejected.
T-019 | P15 | Permissions | Unauthorized player cannot command/access. | GameTest | P0 | Not Started | Action denied.
T-020 | P16 | Crisis | Crisis escalates and recovers within bounds. | Simulation | P1 | Not Started | No runaway feedback.
T-021 | P17 | Performance | 100 residents remain inside tick budget. | Benchmark | P0 | Not Started | Documented budget met.
T-022 | P18 | Compatibility | Supported dependency matrix passes slice. | Matrix CI | P0 | Not Started | Every published combo passes.
T-023 | P18 | Legal | Every adapted file has manifest/header. | CI | P0 | Not Started | No orphaned derivative.
T-024 | P18 | Assets | Forbidden asset scanner is clean. | CI | P0 | Not Started | Only original CIVITAS assets.

## Licenses
Project | Code License | Asset License | Use | Copy Code | Copy Assets | Required Action
Immersive EGO: CIVITAS | GPL-3.0-only | Original | Main project | N/A | Original only | Publish corresponding source and notices.
MineColonies | GPL-3.0 | Audit before copying | Required runtime + adaptation | Yes with provenance | No by default | Record commit/path/copyright/modifications.
MCA Reborn | GPL-3.0-only | Audit specific assets | Required runtime + adaptation | Yes with provenance | No by default | Preserve notices and social-system lineage.
Modern Companions | GPL-3.0-only | Mixed/lineage audit | Required runtime + adaptation | Only after lineage verification | No | Resolve artifact/source and Human Companions/Basic Weapons origins.
Immersive EGO | MIT | Separated | Required runtime API | Prefer API | No | Never send GPL code into MIT repo.
MineColonies dependencies | Per-project audit | Per-project audit | Separate runtime jars | No without audit | No | Audit independently.
Logos/trademarks | N/A | Copyright/trademark | Identification only | N/A | No | Use original CIVITAS branding.

## Configuration
Config File | Key | Type | Default | Reload Level | Description
immersive_civitas-core.toml | core.enabled | boolean | true | LIVE | Master switch.
immersive_civitas-core.toml | core.preset | enum | IMMERSIVE | WORLD_RELOAD | CASUAL/IMMERSIVE/HARDCORE/CUSTOM.
immersive_civitas-residents.toml | residents.scanIntervalTicks | int | 40 | LIVE | Host reconciliation interval.
immersive_civitas-residents.toml | residents.autoRepairStaleLinks | boolean | true | LIVE | Repair stale IDs.
immersive_civitas-minecolonies.toml | minecolonies.externalCitizenProxyEnabled | boolean | true | WORLD_RELOAD | Enable external workers.
immersive_civitas-minecolonies.toml | minecolonies.strictVersionPin | boolean | true | GAME_RESTART | Reject unknown internals.
immersive_civitas-mca.toml | mca.familyAuthority | enum | MCA | GAME_RESTART | Never duplicate family truth.
immersive_civitas-mca.toml | mca.recruitmentMinimumHearts | int | 20 | LIVE | Relationship gate.
immersive_civitas-companions.toml | combat.friendlyFirePolicy | enum | FACTION_AND_FAMILY_SAFE | LIVE | Target safety.
immersive_civitas-companions.toml | combat.safeRecallDistance | int | 40 | LIVE | Recall threshold.
immersive_civitas-work.toml | work.baseUpdateIntervalTicks | int | 20 | LIVE | Planner interval.
immersive_civitas-work.toml | work.minimumReadiness | double | 0.25 | LIVE | Nonessential work refusal threshold.
immersive_civitas-work.toml | work.allowChildrenHazardousJobs | boolean | false | WORLD_RELOAD | Safety gate.
immersive_civitas-logistics.toml | logistics.reservationTimeoutTicks | int | 12000 | LIVE | Stale transaction timeout.
immersive_civitas-logistics.toml | logistics.repairOnServerStart | boolean | true | GAME_RESTART | Repair ledger.
immersive_civitas-economy.toml | economy.dynamicPricing | boolean | true | LIVE | Stock/context pricing.
immersive_civitas-economy.toml | economy.maxPriceMultiplier | double | 4.0 | LIVE | Inflation cap.
immersive_civitas-reputation.toml | reputation.decayIntervalTicks | int | 24000 | LIVE | Slow decay.
immersive_civitas-reputation.toml | reputation.fearCanReplaceTrust | boolean | false | LIVE | Prevent stable fear rule.
immersive_civitas-factions.toml | factions.maxRelationsPerSettlement | int | 128 | WORLD_RELOAD | Graph bound.
immersive_civitas-cultures.toml | culture.changeRate | double | 0.001 | LIVE | Slow cultural change.
immersive_civitas-defense.toml | defense.civilianShelterEnabled | boolean | true | LIVE | Threat response.
immersive_civitas-defense.toml | defense.guardFatigueMatters | boolean | true | LIVE | Use EGO readiness.
immersive_civitas-family.toml | family.keepHouseholdTogetherOnMigration | boolean | true | LIVE | Family migration.
immersive_civitas-governance.toml | governance.legitimacyEnabled | boolean | true | WORLD_RELOAD | Political simulation.
immersive_civitas-crises.toml | crises.maxConcurrentPerSettlement | int | 3 | LIVE | Crisis bound.
immersive_civitas-performance.toml | performance.nearResidentBudgetPerTick | int | 32 | LIVE | Detailed AI budget.
immersive_civitas-performance.toml | performance.unloadedSimulationIntervalTicks | int | 2400 | LIVE | Abstract simulation.
immersive_civitas-performance.toml | performance.maxPathRequestsPerTick | int | 8 | LIVE | Pathfinding budget.

## Release
Checklist ID | Item | Priority | Status | Evidence | Owner
REL-001 | Source and binary version match | P0 | Not Started |  | Codex + Maintainer
REL-002 | GPL license included | P0 | Not Started |  | Codex + Maintainer
REL-003 | Corresponding source generated | P0 | Not Started |  | Codex + Maintainer
REL-004 | THIRD_PARTY_NOTICES complete | P0 | Not Started |  | Codex + Maintainer
REL-005 | All adapted files in manifest | P0 | Not Started |  | Codex + Maintainer
REL-006 | No unapproved assets | P0 | Not Started |  | Codex + Maintainer
REL-007 | Supported dependency versions documented | P0 | Not Started |  | Codex + Maintainer
REL-008 | Unknown versions rejected clearly | P0 | Not Started |  | Codex + Maintainer
REL-009 | Clean build succeeds | P0 | Not Started |  | Codex + Maintainer
REL-010 | Dedicated server starts | P0 | Not Started |  | Codex + Maintainer
REL-011 | Client starts | P0 | Not Started |  | Codex + Maintainer
REL-012 | Vertical slice passes | P0 | Not Started |  | Codex + Maintainer
REL-013 | GameTests pass | P0 | Not Started |  | Codex + Maintainer
REL-014 | JUnit tests pass | P0 | Not Started |  | Codex + Maintainer
REL-015 | Migration tests pass | P0 | Not Started |  | Codex + Maintainer
REL-016 | Duplication stress tests pass | P0 | Not Started |  | Codex + Maintainer
REL-017 | 100-resident performance gate passes | P0 | Not Started |  | Codex + Maintainer
REL-018 | Config reference complete | P1 | Not Started |  | Codex + Maintainer
REL-019 | en_us/fr_fr complete | P1 | Not Started |  | Codex + Maintainer
REL-020 | README/README_FR complete | P1 | Not Started |  | Codex + Maintainer
REL-021 | CurseForge copy complete | P1 | Not Started |  | Codex + Maintainer
REL-022 | Credits complete | P0 | Not Started |  | Codex + Maintainer
REL-023 | No affiliation claim | P0 | Not Started |  | Codex + Maintainer
REL-024 | Upgrade/rollback guide complete | P1 | Not Started |  | Codex + Maintainer
REL-025 | Crash-report guide complete | P2 | Not Started |  | Codex + Maintainer